**UPLIFT MEDICARE WORK PLAN**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Section** | **Activity To Be Done** | **Process Of Achievement** | **Timeline For Completion** | **Stage Completion Charge** |
| Patient | Authentication(Login and Sign Up)  Patient Dashboard  Call A Doctor | -  - | Completed  Completed | -  - |
| Patient | Self Examination | React for frontend and Axios to push the derived form data to the database | 30th November 2022 | UGX 650,000 |
| Patient | Call An Ambulance | React for frontend and node js for backend | Undefined | Undefined |
| Patient | Book An Appointment | React for frontend and node js for backend | 16th October 2022 | UGX 150,000 |
| Patient | Medical History | React for frontend and node js for backend | 25th October 2022 | UGX 100,000 |
| Doctor | Doctor Dashboard | React for frontend | 2nd November 2022 | UGX 250,000 |
| Doctor | Doctor Clacksheet | React for frontend and node js for backend | 20th December 2022 | UGX 450,000 |
| Doctor | Doctor library |  | 5th December 2022 | UGX 350,000 |
| Doctor | Call a patient | - | Completed | - |
| Doctor | View appointments |  | 15th December 2022 | UGX 100,000 |
| Doctor | Appointment History |  | 25th December 2022 | UGX 100,000 |
| Doctor | Edit Profile |  | 20th December 2022 | UGX 100,000 |
| Doctor | Doctor requirement and application form |  | 10th November 2022 | UGX 150,000 |
| Admin | Admin Dashboard |  | 5th January 2023 | UGX 200,000 |
| Admin | Add and verify doctors |  | 10th January 2023 | UGX 450,000 |
| Admin | View users and doctors data |  | 20th January 2023 | UGX 150,000 |
| Admin | View appointments |  | 15th January 2023 | UGX 100,000 |
| Production building and hosting | Production building and hosting | - | 25th January 2023 | UGX 100,000 |
|  |  |  | **TOTAL: UGX** | **3,400,000** |